## Slide 1
Meeting FCBA / 25.06.2016
EU Hardwoods

## Slide 2: Agenda
25.06.2015 |  |  | 
12:00 – 12:30 |  | Lunch | 
12:30 – 13:00 | WP0 | acceptance of last minutes information on project’s extension, reporting internal reports | HFA
13:00 – 14:30 | WP1 | presentation of recent results CT scanning of beech outlook – next steps – discussion status (deadlines, timetable, costs, problems) | FVA
14:30 – 16:00 | WP2 | status lamella data collection testing plan outlook – next steps – discussion status (deadlines, timetable, costs, problems) | HFA / FCBA
16:00 – 16:30 | WP6 | analysis of data: requirements and approach outlook – next steps – discussion status (deadlines, timetable, costs, problems) | UL

## Slide 3: Agenda
26.06.2015 |  |  | 
09:00 – 09:30 | WP0 | Horizon 2020, ERA, … strategy | 
09:30 – 12:00 | WP3 WP4 WP5 | recent results outlook – next steps – discussion status (deadlines, timetable, costs, problems) | MPA FCBA MPA
12:00 – 12:30 | WP0 | any other business date and place for next meeting | ALL

## Slide 4: WP0 – project extension
  on 31.03.2015 official request for extension until 31.12.2016 sent to WWN secretariat
  FNR and MIZS need official national request
  getting in contact with BMLFUW and ADEME / MAAF for details is advised
Germany – FNR
Slovenia – MIZS
Austria – BMLFUW
France – ADEME / MAAF

## Slide 5: WP0 - general
  contribution to WWN newsletter deadline: 03.08.2015
  1st WWN report period: 01.01.2014 - 31.07.2015 submission deadline: 31.08.2015
  status reports
    basis for WWN reporting
    help to keep track of the project’s progress
    to be prepared and sent to HFA and UL quarterly
  WWN seminar at EMPA 14./15.09.2015 registration is open (http://www.woodwisdom.net/seminar-14-15-sept-2015/)

## Slide 6: WP2

## Slide 7: WP2.1 – survey existing data

## Slide 8: WP2.1 – survey existing data
tension
bending edgewise
European oak (DE/CZ/FR): n = 300
Sweet chestnut (ES): n = 249
Birch (N.N.): n = 40
Beech (DE): n = 21
European oak (AT): n = 345
White oak (US): n = 100
finger joints
European oak: bending = 260 tension = 296
White oak: bending = 140 tension = 100
Sweet chestnut: bending = 212 tension = 109
Birch: bending = 20 tension = 20
Beech: tension = 21
Notes: holzbau.forschungs.gmbh:
BU = 483 / ES = 288 / EI = 80 / EKA = 130 / ROB = 124
origin DE, for approx. 40% no exact sample location is known

## Slide 9: WP2.2

## Slide 10: WP2.2 – test plan
additional testing?
(what / how much / why)
finger-joint data
CLT & glulam data
lamella data
scantling data

## Slide 11: WP2.3

## Slide 12: WP2 – outlook
  fixing allocations
  realization of test plan

## Slide 13: WP2 – status
  cost (16.06.2015) 40.000 € (22%)

## Slide 14: WP0 – strategy
  European interest in research related to hardwood  pro-active positioning for H2020 / ERA / WWN / … ?

## Slide 15
Dipl.-Forstw. Peter Linsenmann
p.linsenmann@holzforschung.at
Tel. +43/1/798 26 23-51
www.holzforschung.at