## time_table
project plan | [9 empty] | milestone
time table acc. to proposal
project | EU Hardwoods | [8 empty] | actual time table
content | European hardwoods for the building sector
date | 2014-03-21
| content | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | responsible
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| reporting (WWN & Lebensministerium) | [36 empty] | HFA | bar: 2015 1; 2016 1; 2016 9
0 | WP0 - management | [36 empty] | HFA, Uni LJ | bar: 2014 3 to 2016 9
1 | WP1 - hardwood resources in Europe | 2014 10: 3; 2015 5: 6; 2015 8: 8; 2016 2: 12 | FVA (lead), FCBA, Uni LJ, BFW
1.1 | quantification of recent resources in Europe | bar: 2014 4 to 2014 12
aims
1.2 | forecast to future resource availability | bar: 2014 10 to 2015 12
aims
1.3 | log quality and roundwood allocation potential | bar: 2014 10 to 2016 2
aims
2 | WP2 - Basic hardwood strength data and grading tools | 2015 3: 4; 2015 6: 7; 2015 11: 10 | HFA (lead), FCBA, Uni LJ, FVA, FVH
2.1 | survey on existing lamella data with respect to species and dimensions | bar: 2014 6 to 2015 1
aims | literature study on existing hardwood (visual, mechanical, grading) data
pt. 1: existing allocations & visual grading rules & machine grading input | bar: 2014 6 to 2014 8
data collection (required main content currently in prepation) | bar: 2014 9 to 2014 12
data verification and discussion on aspired strength class combinations | bar: 2015 1
2.2 | allocation of hardwood lamellas to strength classes, lamella testing if necessary | bar: 2014 9 to 2015 11
aims | "maximized" allocation of hardwoods in EN1912; if necessary, additional testing
decision on allocation based on report only or report to TG1 for EN1912 | bar: 2014 9
allocation based on existing data | bar: 2014 9 to 2014 10
new data (if necessary) | bar: 2014 11
material supply | bar: 2014 12 to 2015 2
visual grading and tensile testing (who is testing what) | bar: 2015 2 to 2015 7
allocation based on existing and new data | bar: 2015 10 to 2015 11
2.3 | consolidate visual grading rules, obstacles machine strength grading | bar: 2015 5 to 2015 11
aims | harmonised visual grading rules; prereq. for mach. strength grading
pt. 2 (attempt to consolidate visual grading rules, obstacles in machine grading) | bar: 2015 5 to 2015 7
compendium hardwood usage | bar: 2015 10 to 2015 11
3 | WP3 - Adhesives for structural hardwood bonding | 2016 3: 16 / 17 | MPA (lead), FCBA, HFA
3.1 | general: adhesives types, integrity tests and quality procedures for hardwoods | bar: 2014 4 to 2014 5; 2015 1 to 2016 8
aims
3.2 | finger-joints: consolidate finger-joint data, influence of size and finger-joint type | bar: 2014 4 to 2016 5
aims
4 | WP4 - Glulam made of hardwoods or hardwoods and softwoods | 2016 2: 13 / 14 | FCBA (lead), HFA, MPA, Uni LJ, Simonin
4.1 | simulation of glued laminated hardwood timber (hom / inhom / hyb) | bar: 2015 1 to 2015 10
aims
4.2 | validation testing for assortment of build-ups (produced under factory conditions) | bar: 2015 1 to 2016 2
aims
5 | WP5 - Cross-laminated hybrid timber | 2015 3: 5; 2015 8: 9; 2015 11: 11 | MPA (lead), CBD
5.1 | out-of plane loading (e.g. floors) | bar: 2014 7 to 2015 9
aims
5.2 | in-plane loading (e.g. walls) | bar: 2014 7 to 2015 4
aims
5.3 | derivation of basic strength profiles and design rules | bar: 2014 10 to 2016 3
aims
6 | WP6 - Dissemination | 2014 3: 2; 2016 2: 15; 2016 6: 18 | Uni LJ
Note on E10: kick-off
Note on L11: hardwood supply of recent resources in Europe
Note on S11: future hardwood supply
Note on V11: hardwood grading regulations in Europe
Note on AB11: log quality and roundwood allocation potential
Note on Q18: survey on existing grading data
Note on T18: grading rules
Note on Y18: lamella allocation
Note on B27: number of specimens graded acc. to which grading rule can be allocated to which D-class
Note on B28: discussion on what to test (species, source, grading rule, dimension, number of specimens)
Note on AC36: report adhesives & finger-jointing
Note on AB41: glulam models - hom - inhom - hyb
Note on Q46: CL hybrid timber model
Note on V46: CLT build ups
Note on Y46: CLT guideline
Note on E53: web page available
Note on AB53: publication
Note on AF53: industries insights